## Training Plan Summary
Indegene Campus-22 - Software Development - Patient Experience (MS Dynamics)
Sl.No | Topic | Duration | Modality | SME's | # Days | Start Date | End Date | Session Timings | Meeting Link
1 | IndeJoin Induction | 16 Hours |  |  | 2 Days | 2022-08-01 | 2022-08-02
2 | Learning Plan Walkthough & Expectations Setting | 1 Hour | VILT - Internal | Zeeshan | 1 Hour | 2022-08-04 |  | 10:30 AM to 11:00 AM
3 | BU Orientation | 2 Hours | VILT - Internal | Bijendra/Kavitha/Paridhi | 2 Hrs | 2022-08-08 |  | 10:30 AM to 11:30 AM
4 | Catalyst & Outlook Walkthrough | 1 Hour | VILT - Internal | Zeeshan | 1 Hour | 2022-08-09 |  | 10:30 AM to 12:00 PM
5 | Pre-Training Evaluation | 2 Hrs | Catalyst |  | 2 Hrs | 2022-08-12 |  | 03:00 PM to 04:55 PM | https://catalyst.indegene.com/ 1. English Language Test - 12 Aug 2022, 3:00 to 3: 50 PM 2. Domain Skills Test - 12 Aug 2022, 4:00 to 4:25 PM 3. MS Dynamics Test - 12 Aug 2022, 4:30 to 4:55 PM
6 | MS Dynamics Training | 104 | VILT-External | Externa Trainer - Abhijit | 13 days | 2022-08-17 | 2022-09-05 | 9:00 AM to 12:00 PM
7 | Leader Connect Session | 30 Mins | VILT - Internal | Bina Patil | 30 Mins | 2022-08-19 |  | 5:30 PM to 6:00 PM
8 | Leader Connect Session | 30 Mins | VILT - Internal | Vishal Shah | 30 Mins | 2022-08-26 |  | 5:30 PM to 6:00 PM
9 | Leader Connect Session | 30 Mins | VILT - Internal | Soundarya Mahalingam | 30 Mins | 2022-09-02 |  | 5:30 PM to 6:00 PM
10 | Action Learning Project - Allocation | 16 Hours |  |  | 2 days | 2022-09-07 | 2022-09-08
11 | Action Learning Project - Evaluation | 4 Hours |  |  | 4 Hours | 2022-09-09
4 Weeks

## Training Schedule
Week # | Day # | Day | Training Date | Training Plan | Training Time | Practice Time
Week-1 | Day-1 | WED | 2022-08-17 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
| Day-2 | THU | 2022-08-18 | Practice & Self-Learning |  | 8 Hrs
| Day-3 | FRI | 2022-08-19 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
Week-2 | Day-4 | MON | 2022-08-22 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
| Day-5 | TUE | 2022-08-23 | Practice & Self-Learning |  | 8 Hrs
| Day-6 | WED | 2022-08-24 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
| Day-7 | THU | 2022-08-25 | Practice & Self-Learning |  | 8 Hrs
| Day-8 | FRI | 2022-08-26 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
Week-3 | Day-9 | MON | 2022-08-29 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
| Day-10 | TUE | 2022-08-30 | Practice & Self-Learning |  | 8 Hrs
| Day-11 | WED | 2022-08-31 | Ganesha Chaturthi Holiday
| Day-12 | THU | 2022-09-01 | Practice & Self-Learning |  | 8 Hrs
| Day-13 | FRI | 2022-09-02 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
| Day-14 | MON | 2022-09-05 | Virtual Instructor-Led Training | 3 Hrs | 5 Hrs
[5 empty] | 24 Hrs | 80 Hrs

## MS Dynamics Learning Plan
MS Dynamics - Patient Experince
Day | Duration | TOPIC | SUB-TOPIC
Day 1 | 3 Hours | Introduction to Low-code, No-Code, Canvas App | Introduction to LCNC
Components of LCNC
LCNC vs Traditional Development
Different LCNC Platform/Tools/Applications
Introduction to Power Apps
Power Apps Building Blocks
Power Apps Component, Connectors
Getting Started with Power Apps
Installation and Configuration
Power App Interface overview and examples
Types of Apps (Canvas/Model-driven/Power Portals)
Introduction to Canvas App
Customize a canvas app in Power Apps
Different controls, templates, screen types
Explore different Connectors, Formulae
Create canvas app using Share point, office 365 connectors
Screen/UI Navigation
Collections, variables (local, global, environment level)
Responsive apps, aspect ratio etc
Canvas app + Power automate integration
Day 2 | 3 Hours | Power Automate | Get started with Power Automate
Introduction to different connectors, actions, triggers etc.
Cloud flow, Automate flows, scheduled flows etc.
Officer365, Azure DevOps, SharePoint, excel, Microsoft Planner, OneNote integrations
Send Email, MS teams’ integration
Build more complex flows with Power Automate
Introduction to business process flows in Power Automate
Create an immersive business process flow in Power Automate
Understand advanced business process flow concepts in Power Automate
Introduction to expressions in Power Automate
Approval flow
Document (Excel, pdf, word) generation/conversion through power automate
Day 3 | 3 Hours | Model Driven apps and Dataverse | Introduction to model-driven apps and its building blocks
Benefits of Model Drive apps and Data Modeling introduction
Introduction to Dataverse
Environment and Solution Management
Organization, Business Unit, User/Teams
Entities, Table creation and setting up relationship
Forms, Component and Layout
Day 4 | 3 Hours | Model Driven apps and Dataverse | Create and manage fields within an table in Microsoft Dataverse
Create and define calculated or rollup fields in Microsoft Dataverse
Types of Fields and when to use
Examples with different scenarios/use case and set up and model data
Get started with security roles in Microsoft Dataverse
Field level, form level, entity level security
Access teams, User groups
Day 5 | 3 Hours | Model Driven apps and Dataverse | Site map configuration with example
Define and create business rules in Microsoft Dataverse
Business Process flows, Actions
Web Resources and different types of resources we can use
Use Javascript in as a form script or as a web resource with example
Here we can consider any (Sale/Service/Marketing) lifecycle example
OOB Workflows + actions
Day 6 | 3 Hours | Model Driven apps and Dataverse | Custom Workflow and how to create it
Introduction to Plugin registration tool
Work flow trigger points
Plugin and pipeline stages
Creating and registering a plugin
Plugin Signing, registering steps and triggers steps etc
Debugging plugin
Difference between plugin and custom workflow
Day 7 | 3 Hours | Power Portal | Power Apps portals architecture
Authentication and user management
Access Microsoft Dataverse in Power Apps portals
Extend Power Apps portals
Build custom Power Apps portals web templates
Power Apps component framework
Build a Power Apps component
Use advanced features with Power Apps component framework
Advantages and comparative analysis with canvas and model drive apps
Power Portal + Power Automate
Authentication types (AD, Certificate based, WS standards)
Work with Web API, Custom API
Different Integration options available
Virtual and dynamic entities
Examples
Day 8 | 3 Hours | Power BI | Introduction to Power BI
Installing and configuration
Power BI Desktop and Power BI Service
Model data in Power BI
Create visualizations and dashboards
Publish and share in Power BI
Examples of Power BI